## Projects
ID | Project | Project Summary Objectives | Lead Councillor | Working Group/Committee | Priority | Started | Target Completion | Completed
P1 | Neighbourhood Plan | Implement a Neighbourhood Plan for tarporley |  | Neighbourhood Plan Steering Group | High | 2013 | 2016-05-01
P2 | Outdoor Sports and Recreation Facilities | Development of outdoor sports and recreation facilities at Brook Road and the Community Centre Field including the existing Childrens Play Area | Andrew Wallace | Outdoor Sports and Recreation Committee | High | 2015
P3 | Time Limited High Street Parking | Implement time limited parking along the High Street shopping zone to improve shopper acces to short term car parking spaces. | Gill Clough | Traffic and Parking Working Group | High | 2016-04-01
P4 | New Tarporley Website | Upgrade the tarporley.org.uk website to include: Phase 1 - Parish Council information, Phase 2 - clubs and organisations, Phase 3 - visitor/tourist information. Website to also assimilate and replace the tarporley.net website. | Gordon Pearson | Website & Local Council Award Scheme Working Group | Medium | 2015-08-01 | 2016-12-01
P5 | Footpath & Rights of Way | Upgrade the Footpath & Rights of Way within Tarporley Parish to improve accessibility and encourage usage. |  | Village Improvement Working Group | Medium | 2014 ??
P6 | Village Square | ??? | Gill Clough | Village Square & Public Art Working Group | ????
P7 | New Long-stay Car park | Provision of new long-stay car park(s) of at least 100 spaces to relieve pressure on village centre car parks. | ??? | Traffic and Parking Working Group | High | ??? | ???
P8 | External Project - Relocation of Tarporley Health Centre and TWMH

## Actions
ID | Action Title | Action Summary Objectives | Source | Related Project / Issue / Risk | Lead Councillor/Officer | Working Group/Committee | Priority | Started | Target Completion | Completed
A1 | Replace footpath styles with gates | Replacing styles on FP4, FP17, FP3, FP6 and FP8 as detailed in David press report of March 2016 presented at PC Meeting 11 April. | PC Meeting 11 April | Footpath & Rights of Way | David Press | Village Improvement Working Group | Medium | 2016-04-01
A2 | Reply to RBL letter | Reply to RBL letter of 7-4-16 as discussed in PC Meeting | PC Meeting 11 April | Ex-RBL Site Sale and Development | Parish Clerk |  | High | 2016-04-11
A3 | Clarify Primary School expansion plans | It was agreed the Clerk should write to the primary school and CW&C education team to clarify the schools expansion plans including what funding is in place. | PC Meeting 11 April | Ex-RBL Site Sale and Development | Parish Clerk |  | High | 2016-04-11
A4 | OSRC - Active Cheshire Support | Investigate funding and support available via Charles Maines of Active Cheshire for the development of sport and recreation facilities | PC Meeting 11 April | Outdoor Sports and Recreation Facilities | Andrew Wallace | OSRC | Medium | 2016-04-11
A5 | OSRC - Project Manager | Investigate employing a Project Manager to advance project and assist with workload | PC Meeting 11 April | Outdoor Sports and Recreation Facilities | Andrew Wallace | OSRC | High | 2016-04-11
A6 | OSRC - Funding Consultant | Investigate employing funding and grant applications expert (quotes have been received from two companies). | PC Meeting 11 April | Outdoor Sports and Recreation Facilities | Andrew Wallace | OSRC | Medium | 2016-04-11
A7 | OSRC - Groundwork | Review performance of Groundwork | PC Meeting 11 April | Outdoor Sports and Recreation Facilities | Andrew Wallace | OSRC | Medium | 2016-04-11
A8 | OSRC - TGMS Report | Reviewed details reports by TGMS on ground conditions and drainage solutions | PC Meeting 11 April | Outdoor Sports and Recreation Facilities | Andrew Wallace | OSRC | High | 2016-04-11
A9 | OSRC - Project Phasing | Prepare realistic phasing proposals to match expected funding. | PC Meeting 11 April | Outdoor Sports and Recreation Facilities | Andrew Wallace | OSRC | Medium | 2016-04-11
A10 | Wayleave Agreement | It was agreed that the Clerk should contact Scottish Power stating the field is not permanent pasture as listed on the agreement but a sports and recreation field, and clarify how the transformer will be made safe. | PC Meeting 11 April | Outdoor Sports and Recreation Facilities | Parish Clerk | OSRC | Medium | 2016-04-11
A11 | Community Defibrilator | Parish Council to purchase the semi automatic defibrillator and outdoor stainless steel cabinet and installation, noting the Tarporley Community Centre Committee will provide funds collected for the project | PC Meeting 11 April | none | Parish Clerk |  | Low | 2016-04-11
A12 | HSBC Letter | Write to HSBC to express their disappointment at the loss of a community amenity in a growing village | PC Meeting 11 April | none | Parish Clerk |  | Low | 2016-04-11
A13 | New Parish Clerk Recruitment | Confirm vacancy notice and advertise for a new Clerk | PC Meeting 11 April | none | ???? |  | High | 2016-04-11
A14 | Village Maintenance Contract | That the Council delegate to the Clerk in consultation with Councillors Ken Parker and Andrew Wallace the awarding of the maintenance contract before the May meeting | PC Meeting 11 April | none | Ken Parker | Village Improvement Working Group |  | 2016-04-11
A15 | Scarecrow Trail | It was agreed that a Scarecrow Trail should be developed in 2017 allowing the Council more time to make the preparations | PC Meeting 11 April | none | James Kennedy | Village Improvement Working Group | Low | 2016-04-12 | Summer 2017
A16 | Christmas Lights | Organise the Christmas Lights and switching on ceremony in co-ordination with other groups in the village | Recurring annually | none | ??? | Christmas Lights Working Group | Medium
A17 | Hanging Baskets | Organise the hanging baskets and flower displays. | Recurring annually | none | ??? | Village Improvement Working Group | Medium
A18 | Village fair | Organise the Parish Council stall for the village fair | Recurring annually | none | ??? |  | Low

## Issues
ID | Issue Title | Issue Type | Description | Related Project | Lead Councillor/Officer | Working Group/Committee | Date raised | Severity | Status Open/Closed | Closure date
I-1 | Ex-RBL Site Sale and Development | Village Development | Sale and development of Ex-RBL Site may result in loss of Bowling Green and/or Allotments |  |  |  | 2015 | High | Open
I-2 | PCSO Provision and Funding | Security | No SLA received for contract renewal in 2016 | [5 empty] | Closed | 2016-04-11
I-3 | Lychgate area re-surfacing | Village Facilities
I-4 | Childrens' Playground Condition | Village Facilities |  | Outdoor Sports and Recreation Facilities | Andrew Wallace | OSRC
I-5
I-6
I-7
I-8
I-9

## Risks
ID | Risk | Category | Proximity | Probability Pre-response | Probability Post-response | Impact Pre-response | Impact Post-response | Response Category | Response | Risk Owner | Working Group/Committee | Date Raised | Status Open/Closed | Closure date
R1 | What might happen | Financial, Legal, Health & Safety, Project Success | How soon might this happen | 1=low to 5=high | 1=low to 5=high | 1=low to 5=high | 1=low to 5=high | avoid, reduce, fallback, transfer, accept or share | What exactly wre we going to do.
R2 | Example - Tarporley does not win the Best Kept Village competition | Project Success | 2016-09-01 | 5 | 2 | 1 | 1 | reduce | Set up a task force to engage the whole village to work on exceeding every judging criteria. |  | Village Improvement Working Group
R3
R4
R5
R6
R7
R8
R9
R10
R11
R12
R13

## Contracts
ID | Contract | Scope | Renewal Date | Current Contactor | Lead Councillor/Officer | Working Group/Committee
C1 | Village Maintenance